## Abstract (hidden)
S. No. | Name of the Agency | No.of ULBs | Total Quantity Awarded (in MT) | Total Quantity remediated till date (in MT) | Balance Quantity (in MT) | % of work | Required Rate of Progress (in MT) | Quantity remediated per day (in MT)
1 | 2 |  | 3 | 4 | 5 | 6
1 | M/s Tharuni Assosiates & Avinash agency, Guntur | 85 | 1944267.31 | 513316.565 | 1430950.745 | 26.4% | 13408.7401 | 4127.415
2 | M/s Zigma global Enviro Solutions Private limited, Erode | 26 | 1447375 | 109879.21 | 1337495.79 | 7.592% | 9981.8966 | 2295.63
3 | M/s Saurashtra Enviro private limited, Gujarat | 11 | 314825 | 24655.135 | 290169.865 | 7.831% | 2171.2069 | 2252.19
4 | M/s Sudhakar Infra Pvt.Ltd. | 1 | 63555 | 48419.49 | 15135.51 | 76.19% | 1412.3333 | 944.11
| Total | 123 | 3770022.31 | 696270.4 | 3073751.91 | 18.47% | 26974.1769 | 9619.345

## Abstract (3)
Agency Wise Legacy Waste Status Abstract as on 15.05.2025
S. No. |  | Name of the Agency | No.of ULBs | Total Quantity Awarded (in MT) | CumulativeQuantity remediated till date (in MT) | Balance Quantity (in MT) | % of work | Required rate of progress per day to complete by 2nd October 2025 (in MT) | No.of Machines Functioning | Capacity of the Functioning Machines (in MT) | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT)
1 |  | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 11
1 | 1a | M/s Tharuni Assosiates, Guntur | 20 | 1309152 | 42465.345 | 1266686.655 | 3.244% | 9091.3333 | 9 | 8300 | 3566.255 | 3354.245 | 2298.735
| 1b | Coastl line (ELURU Cluster) | 11 | 239536 | 0 | 239536 | 0% | 1663.4444 | 0 | 0 | 0 | 0 | 0
| 1c | Green Tech (KADAPA Cluster) | 9 | 219004 | 0 | 219004 | 0% | 1520.8611 | 0 | 0 | 0 | 0 | 0
| 1d | Srinivas (HINDUPUR Cluster) | 6 | 116561 | 0 | 116561 | 0% | 809.4514 | 0 | 0 | 0 | 0 | 0
| 1e | Srinivas Setty (ADDANKI Cluster) | 9 | 237910 | 0 | 237910 | 0% | 1652.1528 | 0 | 0 | 0 | 0 | 0
|  | Sub Total | 55 | 2122163 | 42465.345 | 2079697.655 | 2.001% | 14737.2431 | 9 | 8300 | 3566.255 | 3354.245 | 2298.735
2 |  | M/s Zigma global Enviro Solutions Private limited, Erode | 26 | 1447375 | 109879.21 | 1337495.79 | 7.592% | 10051.2153 | 2 | 2100 | 2324.67 | 2295.63 | 1816.96
3 | 3 | M/s Saurashtra Enviro private limited, Gujarat | 11 | 314825 | 24655.135 | 290169.865 | 7.831% | 2186.2847 | 2 | 3600 | 1845.245 | 2252.19 | 1642.23
|  | New Clusters Total | 92 | 3884363 | 176999.69 | 3707363.31 | 4.557% | 26974.7431 | 13 | 14000 | 7736.17 | 7902.065 | 5757.925
1 |  | M/s Tharuni Assosiates & Avinash agency, Guntur (Old) | 30 | 635115.31 | 470851.22 | 164264.09 | 74.14% | 4410.523 | 5 | 3500 | 267.82 | 773.17 | 545.09
2 |  | M/s Sudhakar Infra Pvt.Ltd. | 1 | 63555 | 48419.49 | 15135.51 | 76.19% | 441.3542 | 2 | 1300 | 936.32 | 944.11 | 896.94
|  | Old Clusters Total | 31 | 698670.31 | 519270.71 | 179399.6 | 74.32% | 4851.8772 | 7 | 4800 | 1204.14 | 1717.28 | 1442.03
|  | Grand Total | 123 | 4583033.31 | 696270.4 | 3886762.91 | 15.19% | 31826.6202 | 20 | 18800 | 8940.31 | 9619.345 | 7199.955
*Note |  | M/s Tharuni Assosiates, Guntur | 50 | 1944267.31 | 513316.565 | 1430950.745 | 26.4% | 13501.8563 | 14 | 11800 |  | 4127.415 | 2843.825
*Note |  | M/s Tharuni Assosiates, Guntur and Sub- Contractor s | 85 | 2757278.31 | 513316.565 | 2243961.745 | 18.62% | 19147.766 | 14 | 11800 |  | 4127.415 | 2843.825

## Abstract (2) (hidden)
Agency Wise Legacy Waste Status Abstract as on 13.05.2025
S. No. | Name of the Agency | No.of ULBs | Total Quantity Awarded (in MT) | Total Quantity remediated till date (in MT) | Balance Quantity (in MT) | % of work | Required rate of progress per day to complete by 2nd October 2025 (in MT) | No.of Machines Functioning | Capacity of the Functioning Machines (in MT) | Quantity remediated Today (in MT)
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | M/s Tharuni Assosiates, Guntur | 55 | 2122163 | #REF! | #REF! | #REF! | 14737.2431 | 8 | 6900 | #REF!
2 | M/s Zigma global Enviro Solutions Private limited, Erode | 26 | 1447375 | 109879.21 | 1337495.79 | 7.592% | 10051.2153 | 2 | 2100 | 2295.63
3 | M/s Saurashtra Enviro private limited, Gujarat | 11 | 314825 | 24655.135 | 290169.865 | 7.831% | 2186.2847 | 2 | 3600 | 2252.19
| New Clusters Total | 92 | 3884363 | #REF! | #REF! | #REF! | 26974.7431 | 12 | 12600 | #REF!
1 | M/s Tharuni Assosiates & Avinash agency, Guntur (Old) | 30 | 635115.31 | 470851.22 | 164264.09 | 74.14% | 4410.523 | 5 | 3500 | 773.17
2 | M/s Sudhakar Infra Pvt.Ltd. | 1 | 63555 | 48419.49 | 15135.51 | 76.19% | 441.3542 | 2 | 1300 | 944.11
| Old Clusters Total | 31 | 698670.31 | 519270.71 | 179399.6 | 74.32% | 4851.8772 | 7 | 4800 | 1717.28
| Grand Total | 123 | 4583033.31 | #REF! | #REF! | #REF! | 31826.6202 | 19 | 17400 | #REF!
*Note | M/s Tharuni Assosiates, Guntur | 85 | 2757278.31 | #REF! | #REF! | #REF! | 19147.766 | 13 | 10400 | #REF!

## Tharuni Associates
Agency Wise Legacy Waste Status Abstract as on 11.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference B/W | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 16 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
M/s Tharuni Associates | M/s Tharuni Assosiates, Guntur | Kadapa Municipal Corporation | 1 | Kadapa | 400000 | 10737.11 | 389262.89 | 2800 | 3 | M1 | 900 | 2025-05-06 | 147 | 2025-09-30 | 1690.28 | 1393.96 | 1204.46 |  | M1 functioning | 0 | [5 empty] | 0 | Work not yet started (Agency is awaiting for permission from municipality's to inauguration and start the work.)
|  | Kadapa Municipal Corporation | [7 empty] | M2 | 1100 | 2025-05-06 |  | 2025-09-30 |  |  |  |  | M2 functioning
|  | Kadapa Municipal Corporation | [7 empty] | M3 | 800 | 2025-05-15 |  | 2025-09-30 |  |  |  |  | M3 errection work is in progress
| M/s Tharuni Assosiates, Guntur | Rajahmundry, Cluster (3 ULBs) | 2 | Srikakulam | 80978 | 5286.895 | 75691.105 | 1500 | 2 | M4 | 800 | 2025-05-05 | 60 | 2025-07-05 | 230.505 | 376.715 | 429.655 |  | M4 is functioning | [7 empty] | Work on Hold (Inauguration is Completeed )
[10 empty] | M5 | 700 | 2025-05-09 |  | 2025-07-05 |  |  |  |  | M5 is functioning
|  | Rajahmundry, Cluster (3 ULBs) | 3 | Vizianagaram | 30604 | 10278.26 | 20325.74 | 800 | 1 | M6 | 800 | 2025-04-26 | 50 | 2025-06-30 | 722.93 | 661.21 | 117.1 |  | M6 functioning
|  | Rajahmundry, Cluster (3 ULBs) | 4 | Rajahmundry | 76735 | 0 | 76735 | 1200 | 2 | M7 | 600 | 2025-05-15 | 70 | 2025-09-30 | 0 | 0 | o |  | Weighbridge under installation
[10 empty] | M8 (M/c) | 600 | 2025-06-01 |  | 2025-09-30 |  |  |  |  | M8 Machinery will be shifted from Gollaprolu
|  | Total |  |  | 188317 | 15565.155 | 172751.845 | 3500 | 5 | 0 | 2900 |  | 180 |  | 953.435 | 1037.925 | 546.755 |  | 0 | 0
| M/s Tharuni Assosiates, Guntur | Kakinada, Cluster (3 ULBs) | 5 | Kakinada | 300000 | 1548.97 | 298451.03 | 3400 | 3 | M9 | 900 | 2025-05-15 | 138 | 2025-09-30 | 202.38 | 233.16 | 212.31 |  | Machinery under installation | [7 empty] | 1. Trail run Completed. 2.Processing of Legacy waste to be started.
|  | Kakinada, Cluster (3 ULBs) | [7 empty] | M10 | 1100 | 2025-05-05 |  | 2025-09-30 |  |  |  |  | M10 is Functioning
|  | Kakinada, Cluster (3 ULBs) | [7 empty] | M11 | 1400 | 2025-05-20 |  | 2025-09-30 |  |  |  |  | Machinery in transit & to be installed
|  | Kakinada, Cluster (3 ULBs) | 6 | Palacole | 30000 | 0 | 30000 | 600 | 1 | M19 | 600 | 2025-05-20 | 55 | 2025-09-30 | 0 | 0 | 0 |  | Machinery under installation
|  | Kakinada, Cluster (3 ULBs) | 7 | Amalapuram | 27543 | 1137.75 | 26405.25 | 600 | 1 | M12 | 600 | 2025-05-11 | 50 | 2025-09-30 | 261.04 | 354.83 | 335.21 |  | M12 is Functioning | [7 empty] | Work not yet started (Agency is awaiting for permission from municipality's to inauguration and start the work.)
|  | Total |  |  | 357543 | 2686.72 | 354856.28 | 4600 | 5 | 0 | 4600 |  | 243 |  | 463.42 | 587.99 | 547.52 |  | 0 | 0
| M/s Tharuni Assosiates, Guntur | Chilakaluripeta, Cluster (13 ULBs) | 8 | Chilakaluripet | 166278 | 0 | 166278 | 800 | 1 | M14 | 800 | 2025-05-15 | 120 | 2025-09-30 | 0 | 0 | 0 |  | Electrical connections under progress
|  | Chilakaluripeta, Cluster (13 ULBs) | [5 empty] | 800 | 1 | M6(M/C) | 800 | 2025-07-15 |  | 2025-09-30 |  |  |  |  | M/c will be shifted from Vizainagaram on 03.07.2025
|  | Chilakaluripeta, Cluster (13 ULBs) | 9 | Guntur | 43811 | 13367.33 | 30443.67 | 900 | 1 | M13 | 900 | 2025-04-09 | 40 | 2025-09-30 | 350.09 | 334.37 | 0 |  | Work is in Progress
|  | Chilakaluripeta, Cluster (13 ULBs) | 10 | Narsaraopet | 30609 | 0 | 30609 | 600 | 1 | M17 (M/c) | 600 | 2025-06-15 | 60 | 2025-09-30 | 0 | 0 | 0 |  | 1.M/c will be shifted from Jangareddigudem 2.Vinukonda Material(11195) will be shifted 01-07-205
|  | Chilakaluripeta, Cluster (13 ULBs) | [5 empty] | 1100 | 1 | M18 (M/c) | 1100 | 2025-07-15 |  | 2025-09-30 |  |  |  |  | 1.M/c will be shifted from Ramachandrapuram 2.Piduguralla Material (10793) will be shifted to Narasaraopet from 01-07-2025
|  | Chilakaluripeta, Cluster (13 ULBs) | 11 | Bapatla | 46264 | 109.03 | 46154.97 | 1400 | 1 | M15 | 1400 | 2025-05-14 | 40 | 2025-06-30 | 109.03 | 0 | 0 |  | M15 is functioning
|  | Chilakaluripeta, Cluster (13 ULBs) | 12 | Macherla | 30894 | 0 | 30894 | 600 | 1 | M16 | 600 | 2025-05-25 | 60 | 2025-07-30 | 0 | 0 | 0 |  | Dachepalli materia(6194)l will be shifted to Macherla from 15-07-2025 Gurazala material will be shifted to Macherla
|  | Chilakaluripeta, Cluster (13 ULBs) | 13 | Piduguralla | 10793 | 0 | 10793 |  |  | M17(s) | 600 | 01--7-2025 |  | 2025-09-30 | 0 | 0 | 0 |  | Piduguralla Material will be shifted to Narasaraopet
|  | Chilakaluripeta, Cluster (13 ULBs) | 14 | Vinukonda | 11195 | 0 | 11195 |  |  | M17(s) | 600 | 01--7-2025 |  | 2025-09-30 | 0 | 0 | 0 |  | Vinukonda qty will be shifted to Narasaraopet
|  | Chilakaluripeta, Cluster (13 ULBs) | 15 | Dachepalli | 6194 | 0 | 6194 |  |  | M16 (s) | 600 | 2025-07-15 | 15 | 2025-07-30 | 0 | 0 | 0 |  | Dachepalli qty will be shifted to Macherla
|  | Chilakaluripeta, Cluster (13 ULBs) | 16 | Ponnuru | 8376 | 0 | 8376 |  |  | M13 (S) | 900 | 2025-06-21 | 10 | 2025-06-30 | 0 | 0 | 0 |  | Ponnuru material will be shifted to Guntur
|  | Chilakaluripeta, Cluster (13 ULBs) | 17 | Repalle | 7203 | 0 | 7203 |  |  | M15 (S) | 1400 | 2025-06-15 | 10 | 2025-06-30 | 0 | 0 | 0 |  | Repalle qty will be shifted to Bapatla
|  | Chilakaluripeta, Cluster (13 ULBs) | 18 | Gurazala | 1675 | 0 | 1675 |  |  | M16(s) | 600 | 2025-07-20 | 10 | 2025-07-30 | 0 | 0 | 0 |  | Gurazala qty will be shifted to Macherla
|  | Chilakaluripeta, Cluster (13 ULBs) | 19 | Sattenapalle | 0 | 0 | 0 |  |  | - |  |  |  |  | 0 | 0 | 0
|  | Chilakaluripeta, Cluster (13 ULBs) | 20 | Mangalagiri Tadepalli | 0 | 0 | 0 |  |  | - |  |  |  |  | 0 | 0 | 0
| Total |  |  |  | 363292 | 13476.36 | 349815.64 | 6200 | 7 | 0 | 10900 |  |  |  | 459.12 | 334.37 | 0 |  | 0 | 0
| New Clusters Total |  |  |  | 1309152 | 42465.345 | 1266686.655 | 17100 | 20 | 0 | 19300 |  |  |  | 3566.255 | 3354.245 | 2298.735
| M/s Tharuni Assosiates, Guntur | Cluster 01 | 1 | Yelamanchili | 8719 | 8719 | 0 | - | - | - | - | - | - | - |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 2 | Pithapuram | 24910 | 24910 | 0 | - | - | - | - | - | - | - |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 3 | Peddapuram | 19612 | 19612 | 0 | - | - | - | - | - | - | - |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 4 | Rajam | 12849.14 | 12849.14 | 0 | - | - | - | - | - | - | - |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 5 | Tuni | 22097.82 | 22097.82 | 0 | - | - | M25 | - | - | - | - |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 6 | Samalkot | 37786 | 37786 | 0 | - | - | M26 | - | - | - | - |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 7 | Bobbili | 14711 | 12946.88 | 1764.12 |  | 1 | M24 | 600 | - |  | 30.05.2025 |  | 121.15 | 0 |  | Work in progress | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 01 | 8 | Gollaprolu NP | 13135 | 10889.71 | 2245.29 |  | 1 | M8 | 600 |  |  | 30.05.2025 |  | 87.15 | 0 |  | Work in progress | [6 empty] | 0 | 181.53 | 262.03 | 0
|  | Cluster 01 | 9 | Amadalavalasa | 6678.68 | 0 | 6678.68 |  |  | M4(S) | 800 | 20.06.2025 | 15 | 05.07.2025 |  | 0 | 0 |  | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 10 | Ichapuram | 6260 | 0 | 6260 |  |  | M4(S) | 800 | 20.06.2025 | 15 | 05.07.2025 |  | 0 | 0 |  | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 11 | Palasa -Kasibugga | 9625.88 | 0 | 9625.88 |  |  | M4(S) | 800 | 15.06.2025 | 20 | 05.07.2025 |  | 0 | 0 |  | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 12 | Parvathipuram | 11921.09 | 0 | 11921.09 |  |  | M24(S) | 600 | 01.06.2025 | 20 | 20.06.2025 |  | 0 | 0 |  | Material will be shifted to Bobbili | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 01 | 13 | Salur | 12042 | 0 | 12042 |  |  | M24(S) | 600 | 15.06.2025 | 20 | 05.07.2025 |  | 0 | 0 |  | Material will be shifted to Bobbili | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 01 | 14 | Palakonda | 7700 | 0 | 7700 |  |  | M4(S) | 800 | 15.06.2025 | 20 | 05.07.2025 |  | 0 | 0 |  | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 15 | Nellimarla | 7727.4 | 0 | 7727.4 |  |  | M6(S) | 800 | 2025-06-10 | 20 | 2025-06-30 |  | 0 | 0 |  | Material will be shifted to Vizainagaram |  |  | 20 | 2025-06-30 | Qty will be Shifted to Vizianagaram |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 16 | Narsipatnam | 6250 | 0 | 6250 |  |  | M25(S) | 600 | 15.05.2025 | 20 | 2025-06-30 |  | 0 | 0 |  | Material Will be shifted to Tuni |  |  |  | 15.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Narsipatnam Material will be shifted to Tuni
[5 empty] | 222025.01 | 149810.55 | 72214.46 | 0 | 2 | 0 | 7000 | 2025-06-10 | 150 | 2150-12-30 |  | 208.3 | 0 |  | 0 | 0 | 0 | #VALUE! | 229558 | 0 | 0 | 0 | 181.53 | 262.03 | 0 | 0 | 0 | 0 | 0 | 0
| M/s Tharuni Assosiates, Guntur | Cluster 02 | 17 | Nidadavole | 37207.27 | 37207.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 18 | Tanuku | 74206 | 74206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 19 | Ramachandra-puram | 22142.68 | 0 | 22142.68 |  | 1 | M18 | 1100 |  |  | 01.07.2025 |  | 0 | 0 |  | Work is in Progress | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 20 | Yeleswaram | 11022 | 0 | 11022 |  |  | M26(S) | 600 | 15.05.2025 |  | 10.06.2025 |  | 0 | 0 |  | Material will be shifted to samalkota |  |  |  | 15.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Yelleswaram Material will be shifted to Samalkota
|  | Cluster 02 | 21 | Mandapeta | 8779 | 0 | 8779 |  |  | M18(S) | 1100 | 20.06.2025 |  | 01.07.2025 |  | 0 | 0 |  | Material will be shifted to Ramchandra puram | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 22 | Mummidivaram | 5624 | 0 | 5624 |  |  | M12(S) | 600 | 2025-09-15 |  | 2025-09-30 |  | 0 | 0 |  | Material will be shifted to Amalapuram |  |  | 15 | 2025-09-30 | Qty will be Shifted to Amalapuram |  | 0 | 0 | 0 | 0
[5 empty] | 158980.95 | 111413.27 | 47567.68 | 0 | 1 | 0 | 3400 |  | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 15 | 45930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Avinash agency | Cluster 03 | 23 | YSR Tadigadapa | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 24 | Tiruvuru | 20842 | 20842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Nuzvid | 15995 | 15995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Kondapalli | 4925 | 4925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Palacole | 25181 | 25181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Kovvur | 8775.13 | 8775.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Amalapuram | 27910.22 | 27910.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 25 | Narsapur | 51312 | 39393.02 | 11918.98 | 600 | 1 | M27 | 600 |  |  | 30.09.2025 |  | 564.87 | 545.09 |  | M27 is functioning |  |  |  | 15.07.2025 |  |  | 394.4 | 562.24 | 510.27 | 0 | [5 empty] | Work in progress
|  | Cluster 03 | 26 | Jangareddygudem | 18736 | 16606.03 | 2129.97 | 600 | 1 | M17 | 600 |  |  | 10.06.2025 |  | 0 | 0 |  | Work in progress | [6 empty] | 0 | 210.47 | 0 | 0
|  | Cluster 03 | 27 | Akiveedu | 7312 | 0 | 7312 |  |  | M21(S) | 500 | 15.09.2025 | 15 | 30.09.2025 |  | 0 | 0 |  | Material will be shifted to Bhimavaram |  |  | #VALUE! | 2025-09-30 |  |  | 0 | 0 | 0 | 0
|  | Cluster 03 | 28 | Chintalapudi | 7300 | 0 | 7300 |  |  | M17(S) |  | 25.05.2025 |  | 10.06.2025 |  | 0 | 0 |  | Material will be shifted to Jangareddy Gudem | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 29 | Vuyyuru | 10000 | 0 | 10000 |  |  | M28(S) | 400 | 01.07.2025 |  | 30.07.2025 |  | 0 | 0 |  | Material Will be shifted to Pedana |  |  |  | 31.07.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Vuyyuru material will be shifted to Pedana
|  | Cluster 03 | 30 | Pedana | 5821 | 0 | 5821 | 400 | 1 | M28 | 400 | 25.05.2025 |  | 10.07.2025 |  | 0 | 0 |  | Erection Work in Progress |  |  |  | 30.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Erection Work in Progress
[5 empty] | 254109.35 | 209627.4 | 44481.95 | 1600 | 3 | 0 | 2500 | 0 | 15 | 0 |  | 564.87 | 545.09 |  | 0 | 0 | 0 | #VALUE! | 45930 | 0 | 0 | 394.4 | 772.71 | 510.27 | 0 | 0 | 0 | 0 | 0 | 0
|  | Old clusters Total |  |  | 635115.31 | 470851.22 | 164264.09 | 1600 | 6 | 0 | 12900 |  |  |  |  | 773.17 | 545.09 |  | 0 | 0 | 0 | #VALUE! | 321418 | 0 | 0 | 394.4 | 954.24 | 772.3 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total |  |  | 1944267.31 | 513316.565 | 1430950.745 | 18700 | 26 | 0 | 32200 |  |  |  |  | 4127.415 | 2843.825

## Coastline (ELURU Cluster)
Agency Wise Legacy Waste Status Abstract as on 11.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference B/W | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 15 | 16 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
| Tharuni Assosiates-Coastline | Eluru, Cluster (11 ULBs) | 1 | Eluru | 53348 | 0 | 53348 | 960 | 2 | C-M1 | 480 | 2025-05-17 | 90 | 2025-08-28 | 0 | 0 | 0 |  | C-M1 is in site Under refurbish | 0 | [5 empty] | 0
|  | Eluru, Cluster (11 ULBs) | [7 empty] | C-M2 | 480 | 2025-05-30
|  | Eluru, Cluster (11 ULBs) | 2 | Gudivada | 42953 | 0 | 42953 | 480 | 1 | C-M3 | 480 | 2025-05-20 | 120 | 2025-09-17 | 0 | 0 | 0 |  | C-M3 is in transit, Will be reached by 12.05.2025 | 0 | [5 empty] | 0
|  | Eluru, Cluster (11 ULBs) | 3 | Machilipatnam | 41861 | 0 | 41861 | 960 | 2 | C-M4 | 480 | 2025-05-16 | 80 | 2025-08-04 | 0 | 0 | 0 |  | C-M4 machine Under installation | 0 | [5 empty] | 0
|  | Eluru, Cluster (11 ULBs) | [7 empty] | C-M5 | 480 | 2025-05-30
|  | Eluru, Cluster (11 ULBs) | 4 | Bhimavaram | 32358 | 0 | 32358 | 1000 | 2 | M20 | 500 | 2025-07-01 | 91 | 2025-09-30 | 0 | 0 | 0 |  | Machine to be arrived at 20.05.2025 | 0 | [5 empty] | 0
|  | Eluru, Cluster (11 ULBs) | [7 empty] | M21 | 500 | 2025-07-01
|  | Eluru, Cluster (11 ULBs) | 5 | Tadepalligudem | 30258 | 0 | 30258 |  |  | M22 | 500 | 2025-06-15 |  | 2025-09-30 | 0 | 0 | 0 |  | New machine arrived from Ponnur | 0 | [5 empty] | 0
|  | Eluru, Cluster (11 ULBs) | 6 | Vijayawada | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0
|  | Eluru, Cluster (11 ULBs) | 7 | Jaggaiahpet | 12987 | 0 | 12987 |  |  | C-M4 (M/C) | 480 | 2025-08-20 | 28 | 2025-09-17 | 0 | 0 | 0 |  | C-M4 Machinery will be shifted from Machilipatnam | 0 | [5 empty] | 0
|  | Eluru, Cluster (11 ULBs) | 8 | Kondapalli | 5000 | 0 | 5000 | 480 |  | C-M5 (M/C) | 480 | 2025-09-10 | 20 | 2025-09-30 | 0 | 0 | 0 |  | C-M5 Machinery will be shifted from Machilipatnam | 0 | [5 empty] | 0
|  | Eluru, Cluster (11 ULBs) | 9 | Nandigama | 1398 | 0 | 1398 |  | 1 | C-M1 (M/C) | 480 | 2025-09-10 | 10 | 2025-09-20 | 0 | 0 | 0 |  | C-M1 Machinery will be shifted from Eluru | 0 | [5 empty] | 0
|  | Eluru, Cluster (11 ULBs) | 10 | Nuzvid | 18458 | 0 | 18458 |  | 1 | M23 | 400 | 2025-06-15 | 56 | 2025-08-10 | 0 | 0 | 0 |  | New machine arrived from Repalle
|  | Eluru, Cluster (11 ULBs) | 11 | Kovvur | 915 | 0 | 915 |  |  | M7 (S) | 900 | 2025-08-20 | 5 | 2025-08-25 | 0 | 0 | 0 |  | Material (915MT) Will be shifted to Bhimavaram
|  | Total |  |  | 239536 | 0 | 239536 | 3880 | 9 | [5 empty] | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0

## Tharuni (hidden)
Legacy Waste Scheduled timelines for completion of total quantity before 2nd October 2025
Agency | Cluster | ULB | Quantity to be remediated (in MT) | Quantity remediated (in MT) | Quantity remediated upto 30th April (in MT) | Balance Quantity (in MT) | Capacity of Machine per day to be installed (in MT) | No of Machines | Details of Machinery | [8 empty] | Actual Quantity remediated per day (in MT) | No-of days requred for Completion | Expected date of completion | Remarks | 30th April 2025 | 1st May 2025 | 2nd May 2025 | 3rd May 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
[9 empty] | Machine No | Daily capacity | Start date | Machine No | Daily capacity | Start date | Machine No | Daily capacity | Start date
1 | 2 | 3 | 4 | 5 | 5 | 6 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 21 | 22 | 23 | 24 | 25 |  | 26 | 27 | 28 | 20
M/s Tharuni Assosiates, Guntur
M/s Tharuni Associates | Kadapa Municipal Corporation | Kadapa | 400000 | 0 | 0 | 400000 | 2800 | 3 | M1 | 900 | 2025-05-01 | M2 | 1100 | 2025-05-01 | M3 | 800 | 2025-05-01 |  | 152 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0 | As per agency plan of Action Work should be started on 01 may 2025,But work not started.
| Srikakulam | Srikakulam | 80978 | 20.6 | 0 | 80957.4 | 1500 | 2 | M4 | 800 | 2025-05-01 | M5 | 700 | 2025-05-01 |  |  |  |  | 152 | 2025-09-30 |  | 0 | 20.6 | [7 empty] | 20.6 | Work is in Progress,but Processing material is less then the machine Capacity
|  | Ichapuram | 6260 | 0 | 0 | 6260 | [14 empty] | Qty will be Shifted to Srikakulam | 0 | 0 | [7 empty] | 0
|  | Palasa -Kasibugga | 9625.88 | 0 | 0 | 9625.88 | [14 empty] | Qty will be Shifted to Srikakulam | 0 | 0 | [7 empty] | 0
|  | Amadalavalasa | 6947 | 0 | 0 | 6947 | [14 empty] | Qty will be Shifted to Srikakulam | 0 | 0 | [7 empty] | 0
|  | Palakonda | 7700 | 0 | 0 | 7700 | [14 empty] | Qty will be Shifted to Srikakulam | 0 | 0 | [7 empty] | 0
| Total |  | 111510.88 | 20.6 | 0 | 111490.28 | [15 empty] | 0 | 20.6 | [7 empty] | 20.6
| Vizianagaram | Vizianagaram | 30604 | 3086.01 | 2828.35 | 27517.99 | 800 | 1 | M6 | 800 | 2025-04-26 | [7 empty] | 65 | 2025-06-30 |  | 280.18 | 257.66 | [7 empty] | 257.66 | Work is in Progress,but Processing material is less then the machine Capacity
|  | Nellimerla | 7727 | 0 | 0 | 7727 | [14 empty] | Qty will be Shifted to Vizianagaram | 0 | 0 | [7 empty] | 0
| Total |  | 38331 | 3086.01 | 2828.35 | 35244.99 | [15 empty] | 280.18 | 257.66 | [7 empty] | 257.66
| Rajahmundry | Rajahmundry | 76735 | 0 | 0 | 76735 | 1200 | 2 | M7 | 600 | 2025-05-15 | M8 | 600 | 2025-05-15 |  |  |  |  | 138 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Kovvuru | 915 | 0 | 0 | 915 | [14 empty] | Qty will be Shifted to Rahahmundry | 0 | 0 | [7 empty] | 0
| Total |  | 77650 | 0 | 0 | 77650 | [15 empty] | 0 | 0 | [7 empty] | 0
| Kakinada | Kakinada | 300000 | 0 | 0 | 300000 | 3400 | 3 | M9 | 900 | 2025-05-01 | M10 | 1100 | 2025-05-01 | M11 | 1400 | 2025-05-15 |  | 152 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0 | Trail run Completed,Procedding of Legacy yet to start
| Amalapuram | Amalapuram | 27543 | 0 | 0 | 27543 | 600 | 1 | M12 | 600 | 2025-05-01 | [7 empty] | 152 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0 | As per agency plan of Action Work should be started on 01 may 2025,But work not started.
|  | Mumidivaram | 5624 | 0 | 0 | 5624 | [14 empty] | Mumidivaram Qty shifted to amalapuram | 0 | 0 | [7 empty] | 0
| Total |  | 33167 | 0 | 0 | 33167 | [15 empty] | 0 | 0 | [7 empty] | 0
| Guntur | Guntur | 43811 | 11998 | 11998 | 31813 | 900 | 1 | M13 | 900 | 2025-04-09 | [7 empty] | 174 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Ponnur | 8376 | 0 | 0 | 8376 | [14 empty] | Ponnur Qty Shifted to Guntur | 0 | 0 | [7 empty] | 0
| Total |  | 52187 | 11998 | 11998 | 40189 | [15 empty] | 0 | 0 | [7 empty] | 0
| Chilakaluripet | Chilakaluripet | 166278 | 0 | 0 | 166278 | 1600 | 1 | M14 | 800 | 2025-05-05 | M6(M/C) | 800 | 2025-07-15 |  |  |  |  | 148 | 2025-09-30 | M6(M/C) shifted to Chilakaluripet | 0 | 0 | [7 empty] | 0
| Bapatla | Bapatla | 46264 | 0 | 0 | 46264 | 1400 | 1 | M15 | 1400 | 2025-05-01 | [7 empty] | 152 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0 | As per agency plan of Action Work should be started on 01 may 2025,But work not started.
|  | Repalle | 7203 | 0 | 0 | 7203 | [14 empty] | Repalle Qty shifted to Bapatla | 0 | 0 | [7 empty] | 0
| Total |  | 53467 | 0 | 0 | 53467 | [15 empty] | 0 | 0 | [7 empty] | 0
| Macherla | Macherla | 30894 | 0 | 0 | 30894 | 600 | 1 | M16 | 600 | 2025-05-25 | [7 empty] | 128 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Gurazala | 1675 | 0 | 0 | 1675 | [14 empty] | Gurazal Qty shifted to Macherla | 0 | 0 | [7 empty] | 0
|  | Dachepalli | 6194 | 0 | 0 | 6194 | [14 empty] | Dachepalle Qty shifted to Macherla | 0 | 0 | [7 empty] | 0
| Total |  | 38763 | 0 | 0 | 38763 | [15 empty] | 0 | 0 | [7 empty] | 0
| Narasarao pet | Narasarao pet | 30609 | 0 | 0 | 30609 | 1700 | 2 | M17 | 600 | 2025-06-15 | M18 | 1100 | 2025-07-15 |  |  |  |  | 107 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Vinukonda | 11195 | 0 | 0 | 11195 | [14 empty] | Vinukonda qty shifted to Narasaraopet | 0 | 0 | [7 empty] | 0
|  | Piduguralla | 10793 | 0 | 0 | 10793 | [14 empty] | Piduguralla qty shifted to Narasaraopet | 0 | 0 | [7 empty] | 0
| Total |  | 52597 | 0 | 0 | 52597 | [15 empty] | 0 | 0 | [7 empty] | 0
| Palacole | Palacole | 30000 | 0 | 0 | 30000 | 600 | 1 | M19 | 600 | 2025-05-15 | [7 empty] | 138 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
| Bhimavaram | Bhimavaram | 32358 | 0 | 0 | 32358 | 1200 | 1 | M20 | 600 | 2025-07-15 | M21 | 600 | 2025-07-15 |  |  |  |  | 77 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Akividu | 7312 | 0 | 0 | 7312 | [14 empty] | Akeevidu Qty shifted to Bhimavaram | 0 | 0 | [7 empty] | 0
| Total |  | 39670 | 0 | 0 | 39670 | [15 empty] | 0 | 0 | [7 empty] | 0
| Hindupur, Cluster (6 ULBs) | Hindupur | 49020 | 0 | 0 | 49020 | 700 | 1 | M25 | 700 | 2025-05-10 | [7 empty] | 143 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Dharmavaram | 23000 | 0 | 0 | 23000 | 700 | 1 | M26 | 700 | 2025-05-10 | [7 empty] | 82 | 2025-07-31 |  | 0 | 0 | [7 empty] | 0
|  | Kadiri | 20000 | 0 | 0 | 20000 | 700 | 1 | M27 | 700 | 2025-05-10 | [7 empty] | 51 | 2025-06-30 |  | 0 | 0 | [7 empty] | 0
|  | Penukonda | 13578 | 0 | 0 | 13578 |  | 1 | M28 (M/C) | 700 | 2025-06-25 | [7 empty] | 67 | 2025-08-31 | M28(M/C) shifted from Puttaparty | 0 | 0 | [7 empty] | 0
|  | Puttaparthy | 10299 | 0 | 0 | 10299 |  | 1 | M28 | 700 | 2025-05-10 | [7 empty] | 36 | 2025-06-15 |  | 0 | 0 | [7 empty] | 0
|  | Madakasira | 664 | 0 | 0 | 664 |  | 1 | M27 (M/C) | 700 | 2025-07-15 | [7 empty] | 5 | 2025-07-20 | M27(M/C) shifted from Kadiri | 0 | 0 | [7 empty] | 0
| Total |  | 116561 | 0 | 0 | 116561 | 2100 | [14 empty] | 0 | 0 | [7 empty] | 0
| Per day Capacity | [5 empty] | 20400 | [23 empty] | 0
| Addanki, Cluster (9 ULBs) | Ongole | 61929 | 0 | 0 | 61929 | 900 | 1 | K1 | 900 | 2025-05-08 | [7 empty] | 73 | 2025-07-20 |  | 0 | 0 | [7 empty] | 0
|  | Addanki | 58754 | 0 | 0 | 58754 | 700 | 1 | K2 | 700 | 2025-05-08 | [7 empty] | 89 | 2025-08-05 |  | 0 | 0 | [7 empty] | 0
|  | Markapuram | 33877 | 0 | 0 | 33877 | 700 | 1 | K3 | 700 | 2025-05-10 | [7 empty] | 71 | 2025-07-20 |  | 0 | 0 | [7 empty] | 0
|  | Chirala | 28392 | 0 | 0 | 28392 | 700 | 1 | K4 | 700 | 2025-05-10 | [7 empty] | 66 | 2025-07-15 |  | 0 | 0 | [7 empty] | 0
|  | Kandukuru | 26160 | 0 | 0 | 26160 | 700 | 1 | K5 | 700 | 2025-05-25 | [7 empty] | 36 | 2025-06-30 |  | 0 | 0 | [7 empty] | 0
|  | Chimakurthy | 14459 | 0 | 0 | 14459 |  |  | K1(M/C) | 900 | 2025-07-30 | [7 empty] | 20 | 2025-08-19 | K1(M/C) shifted to Chimakurty | 0 | 0 | [7 empty] | 0
|  | Kanigiri | 11662 | 0 | 0 | 11662 |  |  | K2(M/C) | 700 | 2025-06-30 | [7 empty] | 20 | 2025-07-20 | K2(M/C) shifted to Kanigiri | 0 | 0 | [7 empty] | 0
|  | Darsi | 1602 | 0 | 0 | 1602 | 0 |  | K3(S) | 700 | 2025-07-21 | [7 empty] | 3 | 2025-07-24 | Material Shifted to Markapuram | 0 | 0 | [7 empty] | 0
|  | Podili | 1075 | 0 | 0 | 1075 | 0 |  | K4(S) | 700 | 2025-07-16 | [7 empty] | 2 | 2025-07-18 | Material Shifted to Chirala | 0 | 0 | [7 empty] | 0
| Total |  | 237910 | 0 | 0 | 237910 | 3700 | [14 empty] | 0 | 0 | [7 empty] | 0
| Eluru, Cluster (11 ULBs) | Eluru | 53348 | 0 | 0 | 53348 | 960 | 2 | CM1 | 480 | 2025-05-21 | CM2 | 480 | 2025-05-21 |  |  |  |  | 85 | 2025-08-14 |  | 0 | 0 | [7 empty] | 0
|  | Gudivada | 42953 | 0 | 0 | 42953 | 480 | 1 | CM3 | 480 | 2025-05-21 | [7 empty] | 120 | 2025-09-18 |  | 0 | 0 | [7 empty] | 0
|  | Machilipatnam | 41861 | 0 | 0 | 41861 | 960 | 2 | CM4 | 480 | 2025-05-21 | CM5 | 480 | 2025-05-21 |  |  |  |  | 73 | 2025-08-02 |  | 0 | 0 | [7 empty] | 0
|  | Tadepalligudem | 30258 | 0 | 0 | 30258 | 600 | 600 | M22 | 600 | 2025-05-15 | [7 empty] | 138 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Vijayawada | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Jaggaiahpet | 12987 | 0 | 0 | 12987 | 480 | 1 | CM6 | 480 | 2025-08-09 | [7 empty] | 37 | 2025-09-15 |  | 0 | 0 | [7 empty] | 0
|  | Kondapalli | 5000 | 0 | 0 | 5000 |  |  | CM4 (M/C) | 480 | 2025-08-22 | [7 empty] | 15 | 2025-09-06 |  | 0 | 0 | [7 empty] | 0
|  | Nandigama | 1398 | 0 | 0 | 1398 | 480 |  | CM5 | 480 | 2025-08-22 | [7 empty] | 6 | 2025-08-28 |  | 0 | 0 | [7 empty] | 0
|  | Nuzvid | 18458 | 0 | 0 | 18458 |  | 1 | CM6 (M/C) | 480 | 2025-05-21 | [7 empty] | 60 | 2025-07-20 |  | 0 | 0 | [7 empty] | 0
| Total |  | 206263 | 0 | 0 | 206263 | 3960 | [14 empty] | 0 | 0 | [7 empty] | 0
| Kadapa, Cluster (9 ULBs) | Proddatur | 70730 | 0 | 0 | 70730 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Rayachoti | 94604 | 0 | 0 | 94604 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Badvel | 11926 | 0 | 0 | 11926 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Rajampet | 11800 | 0 | 0 | 11800 |  | 600 | M24 | 600 | 2025-05-15 | [7 empty] | 65 | 2025-09-30 |  | 0 | 0 | [7 empty] | 0
|  | Mydukur | 11244 | 0 | 0 | 11244 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Pulivendula | 10000 | 0 | 0 | 10000 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Jammalamadugu | 4916 | 0 | 0 | 4916 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Yerraguntla | 2021 | 0 | 0 | 2021 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Kamalapuram | 1763 | 0 | 0 | 1763 | [15 empty] | 0 | 0 | [7 empty] | 0
| Total |  | 219004 | 0 | 0 | 217241 | [15 empty] | 0 | 0 | [7 empty] | 0
| Total |  | 2173358.88 | 15104.61 | 14826.35 | 2156491.27 | 18160 | 8 | 0 | 3200 | 183130 | 0 | 3000 | 137409 | 0 | 2200 | 91570 | 0 | 590 | 183720 | 0 | 280.18 | 278.26 | [7 empty] | 278.26 | 0
| Cluster-1,2&3 | Yelamanchili | 8718.59 | 8718.59 | 8718.59 | 0 | [15 empty] | 0 | 0 | [7 empty] | 0
|  | Kovvur | 8775.13 | 8775.13 | 8775.13 | 0 | [15 empty] | 1 | 0 | [7 empty] | 0
|  | Amalapuram | 27910.22 | 27910.22 | 27910.22 | 0 | [15 empty] | 2 | 0 | [7 empty] | 0
|  | Nidadavole | 37207.27 | 37207.27 | 37207.27 | 0 | [15 empty] | 3 | 0 | [7 empty] | 0
|  | Pithapuram | 24910 | 24910 | 24910 | 0 | [15 empty] | 5 | 0 | [7 empty] | 0
|  | Peddapuram | 19612 | 19612 | 19612 | 0 | [15 empty] | 6 | 0 | [7 empty] | 0
|  | Rajam | 12829 | 12829 | 12829 | 0 | [15 empty] | 7 | 0 | [7 empty] | 0
|  | Tanuku | 74206 | 74206 | 74206 | 0 | [15 empty] | 8 | 0 | [7 empty] | 0
|  | Tuni | 22097.82 | 22097.82 | 22097.82 | 0 | [15 empty] | 9 | 0 | [7 empty] | 0
|  | Nuzvid | 15994.68 | 15994.68 | 15994.68 | 0 | [15 empty] | 10 | 0 | [7 empty] | 0
|  | Palacole | 25181 | 25181 | 25181 | 0 | [15 empty] | 11 | 0 | [7 empty] | 0
|  | Kondapalli | 4925 | 4925 | 4925 | 0 | [15 empty] | 12 | 0 | [7 empty] | 0
|  | YSR Tadigadapa | 50000 | 50000 | 50000 | 0 | [15 empty] | 13 | 0 | [7 empty] | 0
|  | Tiruvuru | 20842 | 20842 | 20842 | 0 | [15 empty] | 14 | 0 | [7 empty] | 0
|  | Samalkot | 37786 | 37786 | 37786 | 0 | [15 empty] | 15 | 0 | [7 empty] | 0
|  | Bobbili | 14711 | 11983 | 11983 | 2728 | [15 empty] | 16 | 0 | [7 empty] | 0 | Work on Hold dueto rain
|  | Gollaprolu NP | 13135 | 9476.81 | 9476.81 | 3658.19 | [15 empty] | 17 | 0 | [7 empty] | 0
|  | Ramachandrapuram | 22142.68 | 4255.74 | 4255.74 | 17886.94 | [15 empty] | 18 | 0 | [7 empty] | 0
|  | Narsapur | 51312 | 34887.4 | 34493 | 16424.6 | [15 empty] | 19 | 394.4 | [7 empty] | 394.4 | Work is in Progress
|  | Jangareddygudem | 18736 | 15601.44 | 15601.44 | 3134.56 | [15 empty] | 20 | 0 | [7 empty] | 0
|  | Mandapeta | 8779 | 0 | 0 | 8779 | [15 empty] | 21 | 0 | [7 empty] | 0
|  | Yeleswaram | 11022 | 0 | 0 | 11022 | [15 empty] | 22 | 0 | [7 empty] | 0
|  | Parvathipuram | 11921.09 | 0 | 0 | 11921.09 | [15 empty] | 23 | 0 | [7 empty] | 0
|  | Salur | 12042 | 0 | 0 | 12042 | [15 empty] | 24 | 0 | [7 empty] | 0
|  | Narsipatnam | 6250 | 0 | 0 | 6250 | [15 empty] | 25 | 0 | [7 empty] | 0
|  | Pedana | 5821 | 0 | 0 | 5821 | [15 empty] | 26 | 0 | [7 empty] | 0
|  | Chintalapudi | 7300 | 0 | 0 | 7300 | [15 empty] | 27 | 0 | [7 empty] | 0
|  | Vuyyuru | 10000 | 0 | 0 | 10000 | [15 empty] | 28 | 0 | [7 empty] | 0
| Total |  | 584166.48 | 467199.1 | 466804.7 | 116967.38 | [16 empty] | 394.4
| Totals |  | 2757525.36 | 482303.71 | 481631.05 | 2273458.65 | 18160 | 8 | 0 | 3200 | 183130 | 0 | 3000 | 137409 | 0 | 2200 | 91570 | 0 | 590 | 183720 |  |  | 672.66

## Green Tech (KADAPA Cluster)
Agency Wise Legacy Waste Status Abstract as on 11.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference B/W | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 16 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
| Tharuni Assosiates-Green Tech | Kadapa, Cluster (9 ULBs) | 1 | Proddatur | 70730 | 0 | 70730 | [8 empty] | 0 | 0
|  | Kadapa, Cluster (9 ULBs) | 2 | Rayachoti | 94604 | 0 | 94604 | [8 empty] | 0 | 0
|  | Kadapa, Cluster (9 ULBs) | 3 | Badvel | 11926 | 0 | 11926 | 500 | 1 | Kdp-M1 | 500 | 20.05.2025 | 30 | 15.06.2025 |  | 0 | 0 |  | Machine Under Installation
|  | Kadapa, Cluster (9 ULBs) | 4 | Rajampet | 11800 | 0 | 11800 | [8 empty] | 0 | 0
|  | Kadapa, Cluster (9 ULBs) | 5 | Mydukur | 11244 | 0 | 11244 | [8 empty] | 0 | 0
|  | Kadapa, Cluster (9 ULBs) | 6 | Pulivendula | 10000 | 0 | 10000 | [8 empty] | 0 | 0
|  | Kadapa, Cluster (9 ULBs) | 7 | Jammalamadugu | 4916 | 0 | 4916 | [8 empty] | 0 | 0
|  | Kadapa, Cluster (9 ULBs) | 8 | Yerraguntla | 2021 | 0 | 2021 | [8 empty] | 0 | 0
|  | Kadapa, Cluster (9 ULBs) | 9 | Kamalapuram | 1763 | 0 | 1763 | [8 empty] | 0 | 0
|  | Total |  |  | 219004 | 0 | 219004 |  | 1 | [6 empty] | 0 | 0

## Srinivas (HINDUPUR Cluster)
Agency Wise Legacy Waste Status Abstract as on 11.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference B/W | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 16 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
| Tharuni Assosiates-Srinivas | Hindupur, Cluster (6 ULBs) | 1 | Hindupur | 49020 | 0 | 49020 | 700 | 1 | H-M1 | 700 | 2025-05-22 | 69 | 2025-07-30 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0
|  | Hindupur, Cluster (6 ULBs) | 2 | Dharmavaram | 23000 | 0 | 23000 | 700 | 1 | H-M2 | 700 | 2025-05-30 | 41 | 2025-07-10 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0
|  | Hindupur, Cluster (6 ULBs) | 3 | Madakasira | 664 | 0 | 664 | 700 | 1 | H-M3 | 700 | 2025-05-20 | 3 | 2025-05-23 | 0 | 0 | 0
|  | Hindupur, Cluster (6 ULBs) | 4 | Puttaparthy | 10299 | 0 | 10299 | 700 | 1 | H-M4 | 700 | 2025-05-25 | 21 | 2025-06-15 | 0 | 0 | 0
|  | Hindupur, Cluster (6 ULBs) | 5 | Kadiri | 20000 | 0 | 20000 |  | 1 | H-M3 (M/c) | 700 | 2025-05-30 | 36 | 2025-07-05 | 0 | 0 | 0 |  | H-M2 (M/c) shifted from Madakasira | 0 | [5 empty] | 0
|  | Hindupur, Cluster (6 ULBs) | 6 | Penukonda | 13578 | 0 | 13578 | 700 | 1 | H-M5 | 700 | 2025-05-15 | 30 | 2025-06-14 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0
|  | Total |  |  | 116561 | 0 | 116561 | 3500 | 6 | [5 empty] | 0 | 0 | 0 | [8 empty] | 0

## Srinivas setty(ADDANKICluster)
Agency Wise Legacy Waste Status Abstract as on 11.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference B/W | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 16 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
| Tharuni Assosiates-Srinivas setty | Addanki, Cluster (9 ULBs) | 1 | Ongole | 61929 | 0 | 61929 | 900 | 1 | A-M1 | 900 | 2025-05-15 | 66 | 2025-07-20 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 2 | Addanki | 58754 | 0 | 58754 | 700 | 1 | A-M2 | 700 | 2025-05-15 | 82 | 2025-08-05 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 3 | Markapuram | 33877 | 0 | 33877 | 700 | 1 | A-M3 | 700 | 2025-05-15 | 66 | 2025-07-20 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 4 | Chirala | 28392 | 0 | 28392 | 700 | 1 | A-M4 | 700 | 2025-05-15 | 61 | 2025-07-15 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 5 | Kandukuru | 26160 | 0 | 26160 | 700 | 1 | A-M5 | 700 | 2025-05-25 | 36 | 2025-06-30 | 0 | 0 | 0 |  |  | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 6 | Chimakurthy | 14459 | 0 | 14459 |  |  | A-M1(M/C) | 900 | 2025-07-30 | 20 | 2025-08-19 | 0 | 0 | 0 |  | K1(M/C) shifted to Chimakurty | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 7 | Kanigiri | 11662 | 0 | 11662 |  |  | A-M2(M/C) | 700 | 2025-06-30 | 20 | 2025-07-20 | 0 | 0 | 0 |  | K2(M/C) shifted to Kanigiri | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 8 | Darsi | 1602 | 0 | 1602 | 0 |  | A-M3(M/C) | 700 | 2025-07-21 | 3 | 2025-07-24 | 0 | 0 | 0 |  | Material Shifted to Markapuram | 0 | [5 empty] | 0
|  | Addanki, Cluster (9 ULBs) | 9 | Podili | 1075 | 0 | 1075 | 0 |  | A-M4(M/C) | 700 | 2025-07-16 | 2 | 2025-07-18 | 0 | 0 | 0 |  | Material Shifted to Chirala | 0 | [5 empty] | 0
|  | Total |  |  | 237910 | 0 | 237910 | 3700 | 5 | 0 | 6700 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 0

## Zigma
Agency Wise Legacy Waste Details
Agency Name | Cluster | S.No. | Name of the ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Details of Machinery |  |  |  |  | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference b/w Col.11 & Col.15 | Remarks
[9 empty] | No. Machines | Daily capacity | Starting date | No. of days | Completion Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 16 | 16 | 17
M/s Zigma global Enviro Solutions Private limited, Erode | Nellore Municipal Corporation | 1 | Allipuram | 35000 | 14019.38 | 20980.62 | 800 | 1 | M1 | 800 | 2025-04-19 | 57 | 2025-06-15 | 795.67 | 709.64 | 703.96 |  | Machine is functioning
|  |  | Donthali | 289479 | 0 | 289479 | 1400 | 2 | M2 | 600 | 2025-05-15 | 138 | 2025-09-30 | 0 | 0 | 0 |  | Machine Under Installation
[9 empty] | M12 | 800 | [7 empty] | Machine Capacity 800 Mt to be Increased
|  |  |  | 324479 | 14019.38 | 310459.62 | 2200 | 3 |  |  |  | 0 |  | 795.67 | 709.64 | 703.96
M/s Zigma global Enviro Solutions Private limited, Erode | GVMC | 2 | GVMC | 201400 | 95859.83 | 105540.17 | 1300 | 1 | M3 | 1300 | 2025-03-10 | 158 | 2025-08-15 | 1529 | 1585.99 | 1113 |  | Machine is functioning in Day & Night Shifts
M/s Zigma global Enviro Solutions Private limited, Erode | Chittoor, Cluster (6 ULBs) | 3 | Chittoor | 146232 | 0 | 146232 |  |  | M3(M/c) | 1300 | 2025-05-18 | 135 | 2025-09-30 | 0 | 0 | 0 |  | 1.M3 M/c shifted to Chittoor 2.Machine capacity of 2800 Mt to be Increased
|  | 4 | Madanapalle | 27532 | 0 | 27532 | 500 | 1 | M4 | 500 | 2025-05-15 | 46 | 2025-06-30 | 0 | 0 | 0 |  | Agency Waiting for Weighbridge Callibration
|  | 5 | B.Kothakota | 25772 | 0 | 25772 |  |  | M4(S) | 500 | 2025-06-29 | 68 | 2025-09-05 | 0 | 0 | 0 |  | Qty Shifted to Madanapalle
|  | 6 | Punganur | 22945 | 0 | 22945 | 500 | 1 | M5 | 500 | 2025-05-15 | 38 | 2025-06-22 | 0 | 0 | 0 |  | Machine Under Installation
|  | 7 | Kuppam | 20000 | 0 | 20000 | 500 | 1 | M6 | 500 | 2025-05-15 | 46 | 2025-06-30 | 0 | 0 | 0 |  | Machine Under Installation
|  | 8 | Palamaneru | 13177 | 0 | 13177 | 500 | 1 | M7 | 500 | 2025-05-15 | 38 | 2025-06-22 | 0 | 0 | 0 |  | Machine Under Installation
|  |  |  | 255658 | 0 | 255658 | 2000 | [6 empty] | 0 | 0 | 0
M/s Zigma global Enviro Solutions Private limited, Erode | Tirupati, Cluster (6 ULBs) | 9 | Tirupati | 221473 | 0 | 221473 | 1800 | 1 | M8 | 1800 | 2025-05-15 | 128 | 2025-09-20 | 0 | 0 | 0 |  | Machine Under Installation
|  | 10 | Srikalahasti | 50307 | 0 | 50307 | 800 | 1 | M9 | 800 | 2025-05-16 | 65 | 2025-07-20 | 0 | 0 | 0 |  | Machine Under Installation
|  | 11 | Sullurpet | 38261 | 0 | 38261 | 800 | 1 | M10 | 800 | 2025-05-30 | 50 | 2025-07-19 | 0 | 0 | 0 |  | Machine yet to arrived
|  | 12 | Nagari | 21977 | 0 | 21977 |  |  | M4 (M/C)(S) | 500 | 2025-08-07 | 54 | 2025-09-30 | 0 | 0 | 0 |  | Qty shifted to Puttur
|  | 13 | Puttur | 20034 | 0 | 20034 |  |  | M4(M/C) | 500 | 2025-08-20 | 41 | 2025-09-30 | 0 | 0 | 0 |  | M4(M/C) Shifted to Puttur If Madanapalle machine shifted on 05.09.2025, the capacity of machine to be increased to 1500MT or If New Machine is Installed on 15.05.2025 , 600 machine Capacity is required
|  | 14 | Venkatagiri | 15093 | 0 | 15093 | 400 | 1 | M11 | 400 | 2025-05-15 | 36 | 2025-06-20 | 0 | 0 | 0 |  | Machine at to arrived
|  |  |  | 367145 | 0 | 367145 | 3800 | [6 empty] | 0 | 0 | 0
M/s Zigma global Enviro Solutions Private limited, Erode | Nellore, Cluster (6 ULBs) | 15 | Kavali | 18536 | 0 | 18536 |  |  | M5(M/C) | 500 | 2025-06-25 | 64 | 2025-08-28 | 0 | 0 | 0 |  | M5(M/C)Shifted from Punganur
|  | 16 | Gudur(N) | 26563 | 0 | 26563 |  |  | M8(M/C) | 1800 | 2025-08-12 | 44 | 2025-09-25 | 0 | 0 | 0 |  | 500mt Capacity New Machine required
|  | 17 | Atmakur(N) | 12784 | 0 | 12784 |  | 1 | M9(M/C) | 800 | 2025-08-01 | 19 | 2025-08-20 | 0 | 0 | 0 |  | M5(M/C)Shifted from Srikalahasti
|  | 18 | Buchireddypalem | 6030 | 0 | 6030 |  |  | M11 (M/C) | 400 | 2025-06-22 | 23 | 2025-07-15 | 0 | 0 | 0 |  | M5(M/C)Shifted from Venkatagiri
|  | 19 | Naidupet | 4186 | 0 | 4186 |  |  | M8 (M/C)(S) | 1800 | 2025-09-25 | 5 | 2025-09-30 | 0 | 0 | 0 |  | Qty Shifted to Gudur(N)
|  | 20 | Alluru | 908 | 0 | 908 |  |  | M1(S) | 800 | 2025-06-05 | 33 | 2025-07-08 | 0 | 0 | 0 |  | Qty Shifted to Nellore
|  |  |  | 69007 | 0 | 69007 | 0 | [6 empty] | 0 | 0 | 0
M/s Zigma global Enviro Solutions Private limited, Erode | Anantapur, Cluster (6 ULBs) | 21 | Anantapur | 168285 | 0 | 168285 |  |  | M1(M/C) | 1800 | 2025-07-10 | 82 | 2025-09-30 | 0 | 0 | 0 |  | If Nellore machine shifted on 10.07.2025, the capacity of machine to be increased to 1200MT or If New Machine is Installed on 15.05.2025 , 1200 machine Capacity is required
|  | 22 | Tadipatri | 22735 | 0 | 22735 |  |  | M6(M/C) | 500 | 2025-06-25 | 46 | 2025-08-10 | 0 | 0 | 0 |  | M6(M/C) shifted from Kuppam
|  | 23 | Guntakal | 20000 | 0 | 20000 |  |  | M7(M/C) | 500 | 2025-06-25 | 46 | 2025-08-10 | 0 | 0 | 0 |  | M7(M/C) shifted from Palamaneru
|  | 24 | Kalyanadurgam | 7184 | 0 | 7184 |  |  | M9(M/C2) | 800 | 2025-08-10 | 10 | 2025-08-20 | 0 | 0 | 0 |  | New Machine to be Installed
|  | 25 | Rayadurgam | 6919 | 0 | 6919 |  |  | M9(M/C) | 800 | 2025-07-28 | 11 | 2025-08-08 | 0 | 0 | 0 |  | M9(M/C) Shifted from Srikalahasti
|  | 26 | Gooty | 4563 | 0 | 4563 |  |  | M10(M/C) | 400 | 2025-08-15 | 21 | 2025-09-05 | 0 | 0 | 0 |  | M10(M/C) Shifted fromm Sullurpet
|  |  |  | 229686 | 0 | 229686 | 0 | [6 empty] | 0 | 0 | 0
|  |  | Total | 1447375 | 109879.21 | 1337495.79 | 9300 | [6 empty] | 2324.67 | 2295.63 | 1816.96
[12 empty] | 2025-05-25 |  |  | 2025-06-15
[12 empty] | 2025-05-15 |  |  | 2025-06-14

## Saurastra
Agency Wise Legacy Waste Details
Agency | Agency Name | Cluster | S. No. | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Details of Machinery |  |  |  |  | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference b/n Col.11 & Col.15 | Remarks
[10 empty] | No. Machines | Daily capacity | Starting date | No. of days | Completion Date
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 16 | 16 | 17
M/s Saurastra Enviro Pvt Ltd, Gujarat | M/s Saurastra Enviro Pvt Ltd, Gujarat | Kurnool, Cluster (5 ULBs) | 1 | Kurnool | 67308 | 13332.81 | 53975.19 | 1800 | 1 | M1 | 1800 | 29.04.2025 | 45 | 15.06.2025 | 715.115 | 1055.11 | 974.22 |  | Work is in Progress.
|  |  | 2 | Dhone | 50000 | 0 | 50000 | 1800 | 1 | M2 | 1800 | 15.05.2025 | 35 | 30.06.2025 | 0 | 0 | 0 |  | Machine yet to arrive
|  |  | 3 | Yemmiganur | 41357 | 0 | 41357 | 600 | 1 | M3 | 600 | 15.05.2025 | 75 | 20.07.2025 | 0 | 0 | 0 |  | Machine yet to arrive
|  |  | 4 | Adoni | 10000 | 0 | 10000 |  |  | M2 (M/c) | 1800 | 06.07.2025 | 10 | 20.07.2025 | 0 | 0 | 0 |  | M2 M/c will be shifted from Dhone
|  |  | 5 | Gudur(K) | 2666 | 0 | 2666 |  |  | M1(S) | 1800 | 15.06.2025 | 5 | 20.06.2025 | 0 | 0 | 0 |  | Qunatity 2666MT will be shifted to Kurnool
[5 empty] | 171331 | 13332.81 | 157998.19 | 4200 | 3 | [5 empty] | 715.115 | 1055.11 | 974.22
| M/s Saurastra Enviro Pvt Ltd, Gujarat | Nandyal, Cluster (6 ULBs) | 6 | Nandyal | 80083 | 11322.325 | 68760.675 | 1800 | 1 | M4 | 1800 | 28.04.2025 | 50 | 20.06.2025 | 1130.13 | 1197.08 | 668.01 |  | Work is in Progress. Agency Installed new Weighbridge.
|  |  | 7 | Bethamcherla | 24189 | 0 | 24189 | 1200 | 1 | M5 | 1200 | 15.05.2025 | 30 | 10.06.2025 | 0 | 0 | 0 |  | Due to Some Internal Concerns agency planed to machine Install in Nandikotkur (Machine Yet to arrive)
|  |  | 8 | Nandikotkur | 19700 | 0 | 19700 |  |  | M5 (M/c) | 1200 | 15.06.2025 | 20 | 05.07.2025 | 0 | 0 | 0 |  | M5 M/c will be shifted from Bethamcherla
|  |  | 9 | Atmakur(K) | 3596 | 0 | 3596 |  |  | M5 (S) | 1200 | 06.07.2025 | 5 | 10.07.2025 | 0 | 0 | 0 |  | Quantity will be shifted to Nandikotkur
|  |  | 10 | Giddalur | 9773 | 0 | 9773 | 600 | 1 | M6 | 600 | 25.05.2025 | 20 | 30.05.2025 | 0 | 0 | 0 |  | Machine arrived on 20.05.2025
|  |  | 11 | Allagadda | 6153 | 0 | 6153 |  |  | M6 (M/c) | 600 | 06.06.2025 | 15 | 25.06.2025 | 0 | 0 | 0 |  | M6 M/c shifted from Giddalur
[5 empty] | 143494 | 11322.325 | 132171.675 | 3600 | 3 | [5 empty] | 1130.13 | 1197.08 | 668.01
|  |  |  | Total | 314825 | 24655.135 | 290169.865 | 7800 | 6 | [5 empty] | 1845.245 | 2252.19 | 1642.23
[13 empty] | 2025-05-25 |  |  | 2025-06-15
[13 empty] | 2025-05-15 |  |  | 2025-06-14

## Tharuni Associates Old Cluster
Agency Wise Legacy Waste Status Abstract as on 11.05.2025 | Agency Wise Legacy Waste Details
Agency | Agency | Cluster | S.no | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Machine No | Daily capacity | Start date | No-of days requred for Completion | Expected date of completion | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference B/W | Remarks | 30th April 2025 | 4th May 2025 | 5th May 2025 | 6th May 2025 | 7th May 2025 | 8th May 2025 | 1st May to 8th 2025 | Status
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 16 | 16 | 16 | 17 | 21 | 24 | 25 |  | 26 | 27 | 28 | 20
M/s Tharuni Associates | M/s Tharuni Assosiates, Guntur | Kadapa Municipal Corporation | 1 | Kadapa | 400000 | 9046.83 | 390953.17 | 2800 | 3 | M1 | 900 | 45783 | 147 | 45930 |  |  | 1393.96 | 1204.46 |  | M1 functioning | 0 | [5 empty] | 0 | Work not yet started (Agency is awaiting for permission from municipality's to inauguration and start the work.)
|  | Kadapa Municipal Corporation | [7 empty] | M2 | 1100 | 45783 |  | 45930 | [5 empty] | M2 functioning
|  | Kadapa Municipal Corporation | [7 empty] | M3 | 800 | 45792 |  | 45930 | [5 empty] | M3 errection work is in progress
| M/s Tharuni Assosiates, Guntur | Rajahmundry, Cluster (3 ULBs) | 2 | Srikakulam | 80978 | 5056.39 | 75921.61 | 1500 | 2 | M4 | 800 | 45782 | 60 | 45843 |  |  | 376.715 | 429.655 |  | M4 functional is slow due to bad weather conditions | [7 empty] | Work on Hold (Inauguration is Completeed )
[10 empty] | M5 | 700 | 45786 |  | 45843 | [5 empty] | M5 functional is slow due to bad weather conditions
|  | Rajahmundry, Cluster (3 ULBs) | 3 | Vizianagaram | 30604 | 9555.33 | 21048.67 | 800 | 1 | M6 | 800 | 45773 | 50 | 45838 |  |  | 661.21 | 117.1 |  | M6 functioning
|  | Rajahmundry, Cluster (3 ULBs) | 4 | Rajahmundry | 76735 | 0 | 76735 | 1200 | 2 | M7 | 600 | 45792 | 70 | 45930 |  |  | 0 | o |  | Weighbridge under installation
[10 empty] | M8 (M/c) | 600 | 45809 |  | 45930 | [5 empty] | M8 Machinery will be shifted from Gollaprolu
|  | Total |  |  | 188317 | 14611.72 | 173705.28 | 3500 | 5 | 0 | 2900 | 183133 | 180 | 183454 |  |  | 1037.925 | 546.755 |  | 0 | 0
| M/s Tharuni Assosiates, Guntur | Kakinada, Cluster (3 ULBs) | 5 | Kakinada | 300000 | 1346.59 | 298653.41 | 3400 | 3 | M9 | 900 | 45792 | 138 | 45930 |  |  | 233.16 | 212.31 |  | Machinery under installation | [7 empty] | 1. Trail run Completed. 2.Processing of Legacy waste to be started.
|  | Kakinada, Cluster (3 ULBs) | [7 empty] | M10 | 1100 | 45782 |  | 45930 | [5 empty] | M10 is Functioning
|  | Kakinada, Cluster (3 ULBs) | [7 empty] | M11 | 1400 | 45797 |  | 45930 | [5 empty] | Machinery in transit & to be installed
|  | Kakinada, Cluster (3 ULBs) | 6 | Palacole | 30000 | 0 | 30000 | 600 | 1 | M19 | 600 | 45797 | 55 | 45930 |  |  | 0 | 0 |  | Machinery under installation
|  | Kakinada, Cluster (3 ULBs) | 7 | Amalapuram | 27543 | 876.71 | 26666.29 | 600 | 1 | M12 | 600 | 45788 | 50 | 45930 |  |  | 354.83 | 335.21 |  | M12 is Functioning | [7 empty] | Work not yet started (Agency is awaiting for permission from municipality's to inauguration and start the work.)
|  | Total |  |  | 357543 | 2223.3 | 355319.7 | 4600 | 5 | 0 | 4600 | 228956 | 243 | 229650 |  |  | 587.99 | 547.52 |  | 0 | 0
| M/s Tharuni Assosiates, Guntur | Chilakaluripeta, Cluster (13 ULBs) | 8 | Chilakaluripet | 166278 | 0 | 166278 | 800 | 1 | M14 | 800 | 45792 | 120 | 45930 |  |  | 0 | 0 |  | Electrical connections under progress
|  | Chilakaluripeta, Cluster (13 ULBs) | [5 empty] | 800 | 1 | M6(M/C) | 800 | 45853 |  | 45930 | [5 empty] | M/c will be shifted from Vizainagaram on 03.07.2025
|  | Chilakaluripeta, Cluster (13 ULBs) | 9 | Guntur | 43811 | 13017.24 | 30793.76 | 900 | 1 | M13 | 900 | 45756 | 40 | 45930 |  |  | 334.37 | 0 |  | Work is in Progress
|  | Chilakaluripeta, Cluster (13 ULBs) | 10 | Narsaraopet | 30609 | 0 | 30609 | 600 | 1 | M17 (M/c) | 600 | 45823 | 60 | 45930 |  |  | 0 | 0 |  | 1.M/c will be shifted from Jangareddigudem 2.Vinukonda Material(11195) will be shifted 01-07-205
|  | Chilakaluripeta, Cluster (13 ULBs) | [5 empty] | 1100 | 1 | M18 (M/c) | 1100 | 45853 |  | 45930 | [5 empty] | 1.M/c will be shifted from Ramachandrapuram 2.Piduguralla Material (10793) will be shifted to Narasaraopet from 01-07-2025
|  | Chilakaluripeta, Cluster (13 ULBs) | 11 | Bapatla | 46264 | 0 | 46264 | 1400 | 1 | M15 | 1400 | 45791 | 40 | 45838 |  |  | 0 | 0 |  | Repalle material (7203) will be shifted to Bapatla from 15-06-2025
|  | Chilakaluripeta, Cluster (13 ULBs) | 12 | Macherla | 30894 | 0 | 30894 | 600 | 1 | M16 | 600 | 45802 | 60 | 45868 |  |  | 0 | 0 |  | Dachepalli materia(6194)l will be shifted to Macherla from 15-07-2025 Gurazala material will be shifted to Macherla
|  | Chilakaluripeta, Cluster (13 ULBs) | 13 | Piduguralla | 10793 | 0 | 10793 |  |  | M17(s) | 600 | 01--7-2025 |  | 45930 |  |  | 0 | 0 |  | Piduguralla Material will be shifted to Narasaraopet
|  | Chilakaluripeta, Cluster (13 ULBs) | 14 | Vinukonda | 11195 | 0 | 11195 |  |  | M17(s) | 600 | 01--7-2025 |  | 45930 |  |  | 0 | 0 |  | Vinukonda qty will be shifted to Narasaraopet
|  | Chilakaluripeta, Cluster (13 ULBs) | 15 | Dachepalli | 6194 | 0 | 6194 |  |  | M16 (s) | 600 | 45853 | 15 | 45868 |  |  | 0 | 0 |  | Dachepalli qty will be shifted to Macherla
|  | Chilakaluripeta, Cluster (13 ULBs) | 16 | Ponnuru | 8376 | 0 | 8376 |  |  | M13 (S) | 900 | 45829 | 10 | 45838 |  |  | 0 | 0 |  | Ponnuru material will be shifted to Guntur
|  | Chilakaluripeta, Cluster (13 ULBs) | 17 | Repalle | 7203 | 0 | 7203 |  |  | M15 (S) | 1400 | 45823 | 10 | 45838 |  |  | 0 | 0 |  | Repalle qty will be shifted to Bapatla
|  | Chilakaluripeta, Cluster (13 ULBs) | 18 | Gurazala | 1675 | 0 | 1675 |  |  | M16(s) | 600 | 45858 | 10 | 45868 |  |  | 0 | 0 |  | Gurazala qty will be shifted to Macherla
|  | Chilakaluripeta, Cluster (13 ULBs) | 19 | Sattenapalle | 0 | 0 | 0 |  |  | - | [6 empty] | 0 | 0
|  | Chilakaluripeta, Cluster (13 ULBs) | 20 | Mangalagiri Tadepalli | 0 | 0 | 0 |  |  | - | [6 empty] | 0 | 0
| Total |  |  |  | 363292 | 13017.24 | 350274.76 | 6200 | 7 | 0 | 10900 | [5 empty] | 334.37 | 0 |  | 0 | 0
| New Clusters Total |  |  |  | 1309152 | 38899.09 | 1270252.91 | 17100 | 20 | 0 | 19300 | [5 empty] | 3354.245 | 2298.735
| M/s Tharuni Assosiates, Guntur | Cluster 01 | 1 | Yelamanchili | 8719 | 8719 | 0 | - | - | - | - | - | - | - |  |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 2 | Pithapuram | 24910 | 24910 | 0 | - | - | - | - | - | - | - |  |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 3 | Peddapuram | 19612 | 19612 | 0 | - | - | - | - | - | - | - |  |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 4 | Rajam | 12849.14 | 12849.14 | 0 | - | - | - | - | - | - | - |  |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 5 | Tuni | 22097.82 | 22097.82 | 0 | - | - | M25 | - | - | - | - |  |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 6 | Samalkot | 37786 | 37786 | 0 | - | - | M26 | - | - | - | - |  |  | - | - |  | Work Completed | - | - | - | - | - | - | 0 | 0 | 0 | 0
|  | Cluster 01 | 7 | Bobbili | 14711 | 12946.88 | 1764.12 |  | 1 | M24 | 600 | - |  | 30.05.2025 | 0 | 121.15 | 121.15 | 0 |  | Work in progress | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 01 | 8 | Gollaprolu NP | 13135 | 10889.71 | 2245.29 |  | 1 | M8 | 600 |  |  | 30.05.2025 | 0 | 87.15 | 87.15 | 0 |  | Work in progress | [6 empty] | 0 | 181.53 | 262.03 | 0
|  | Cluster 01 | 9 | Amadalavalasa | 6678.68 | 0 | 6678.68 |  |  | M4(S) | 800 | 20.06.2025 | 15 | 05.07.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 10 | Ichapuram | 6260 | 0 | 6260 |  |  | M4(S) | 800 | 20.06.2025 | 15 | 05.07.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 11 | Palasa -Kasibugga | 9625.88 | 0 | 9625.88 |  |  | M4(S) | 800 | 15.06.2025 | 20 | 05.07.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 12 | Parvathipuram | 11921.09 | 0 | 11921.09 |  |  | M24(S) | 600 | 01.06.2025 | 20 | 20.06.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to Bobbili | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 01 | 13 | Salur | 12042 | 0 | 12042 |  |  | M24(S) | 600 | 15.06.2025 | 20 | 05.07.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to Bobbili | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 01 | 14 | Palakonda | 7700 | 0 | 7700 |  |  | M4(S) | 800 | 15.06.2025 | 20 | 05.07.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to Srikkulam |  |  | #VALUE! | 2025-09-30 | Qty will be Shifted to Srikakulam |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 15 | Nellimarla | 7727.4 | 0 | 7727.4 |  |  | M6(S) | 800 | 45818 | 20 | 45838 | 0 | 0 | 0 | 0 |  | Material will be shifted to Vizainagaram |  |  | 20 | 2025-06-30 | Qty will be Shifted to Vizianagaram |  | 0 | 0 | 0 | 0
|  | Cluster 01 | 16 | Narsipatnam | 6250 | 0 | 6250 |  |  | M25(S) | 600 | 15.05.2025 | 20 | 45838 | 0 | 0 | 0 | 0 |  | Material Will be shifted to Tuni |  |  |  | 15.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Narsipatnam Material will be shifted to Tuni
[5 empty] | 222025.01 | 149810.55 | 72214.46 | 0 | 2 | 0 | 7000 | 45818 | 150 | 91676 | 0 | 208.3 | 208.3 | 0 |  | 0 | 0 | 0 | #VALUE! | 229558 | 0 | 0 | 0 | 181.53 | 262.03 | 0 | 0 | 0 | 0 | 0 | 0
| M/s Tharuni Assosiates, Guntur | Cluster 02 | 17 | Nidadavole | 37207.27 | 37207.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 18 | Tanuku | 74206 | 74206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 19 | Ramachandra-puram | 22142.68 | 4255 | 17887.68 |  | 1 | M18 | 1100 |  |  | 01.07.2025 | 0 | 0 | 0 | 0 |  | Work is in Progress | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 20 | Yeleswaram | 11022 | 0 | 11022 |  |  | M26(S) | 600 | 15.05.2025 |  | 10.06.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to samalkota |  |  |  | 15.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Yelleswaram Material will be shifted to Samalkota
|  | Cluster 02 | 21 | Mandapeta | 8779 | 0 | 8779 |  |  | M18(S) | 1100 | 20.06.2025 |  | 01.07.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to Ramchandra puram | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 02 | 22 | Mummidivaram | 5624 | 0 | 5624 |  |  | M12(S) | 600 | 45915 |  | 45930 | 0 | 0 | 0 | 0 |  | Material will be shifted to Amalapuram |  |  | 15 | 2025-09-30 | Qty will be Shifted to Amalapuram |  | 0 | 0 | 0 | 0
[5 empty] | 158980.95 | 115668.27 | 43312.68 | 0 | 1 | 0 | 3400 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 15 | 45930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Avinash agency | Cluster 03 | 23 | YSR Tadigadapa | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 24 | Tiruvuru | 20842 | 20842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Nuzvid | 15995 | 15995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Kondapalli | 4925 | 4925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Palacole | 25181 | 25181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Kovvur | 8775.13 | 8775.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 |  | Amalapuram | 27910.22 | 27910.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work Completed | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 25 | Narsapur | 51312 | 39393.02 | 11918.98 | 600 | 1 | M27 | 600 |  |  | 30.09.2025 | 0 | 564.87 | 564.87 | 545.09 |  | M27 is functioning |  |  |  | 15.07.2025 |  |  | 394.4 | 562.24 | 510.27 | 0 | [5 empty] | Work in progress
|  | Cluster 03 | 26 | Jangareddygudem | 18736 | 16606.03 | 2129.97 | 600 | 1 | M17 | 600 |  |  | 10.06.2025 | 267.82 | 0 | 0 | 0 |  | Work in progress | [6 empty] | 0 | 210.47 | 0 | 0
|  | Cluster 03 | 27 | Akiveedu | 7312 | 0 | 7312 |  |  | M21(S) | 500 | 15.09.2025 | 15 | 30.09.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to Bhimavaram |  |  | #VALUE! | 2025-09-30 |  |  | 0 | 0 | 0 | 0
|  | Cluster 03 | 28 | Chintalapudi | 7300 | 0 | 7300 |  |  | M17(S) |  | 25.05.2025 |  | 10.06.2025 | 0 | 0 | 0 | 0 |  | Material will be shifted to Jangareddy Gudem | [6 empty] | 0 | 0 | 0 | 0
|  | Cluster 03 | 29 | Vuyyuru | 10000 | 0 | 10000 |  |  | M28(S) | 400 | 01.07.2025 |  | 30.07.2025 | 0 | 0 | 0 | 0 |  | Material Will be shifted to Pedana |  |  |  | 31.07.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Vuyyuru material will be shifted to Pedana
|  | Cluster 03 | 30 | Pedana | 5821 | 0 | 5821 | 400 | 1 | M28 | 400 | 25.05.2025 |  | 10.07.2025 | 0 | 0 | 0 | 0 |  | Erection Work in Progress |  |  |  | 30.06.2025 |  |  | 0 | 0 | 0 | 0 | [5 empty] | Erection Work in Progress
[5 empty] | 254109.35 | 209627.4 | 44481.95 | 1600 | 3 | 0 | 2500 | 0 | 15 | 0 | 267.82 | 564.87 | 564.87 | 545.09 |  | 0 | 0 | 0 | #VALUE! | 45930 | 0 | 0 | 394.4 | 772.71 | 510.27 | 0 | 0 | 0 | 0 | 0 | 0
|  | Old clusters Total |  |  | 635115.31 | 475106.22 | 160009.09 | 1600 | 6 | 0 | 12900 |  |  |  | 267.82 | 773.17 | 773.17 | 545.09 |  | 0 | 0 | 0 | #VALUE! | 321418 | 0 | 0 | 394.4 | 954.24 | 772.3 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total |  |  | 1944267.31 | 514005.31 | 1430262 | 18700 | 26 | 0 | 32200 | [5 empty] | 4127.415 | 2843.825

## Sudhakar (2)
Agency Wise Legacy Waste Details
Agency Wise Legacy Waste Status Abstract as on 11.05.2025 | Cluster | S. No. | ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Balance Quantity in MT | Required Rate of Progress (in MT) | No of Machines | Details of Machinery |  |  |  |  | Quantity remediated on 14.05.2025 (in MT) | Quantity remediated on 13.05.2025 (in MT) | Quantity remediated on 12.05.2025 (in MT) | Difference b/n Col.11 & Col.15 | Remarks
[9 empty] | No. Machines | Daily capacity | Start date | No. of days | Expected date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 15 | 16 | 16 | 17
M/s Sudhakar Infra Pvt.Ltd. | Tenali | 1 | Tenali | 63555 | 48419.49 | 15135.51 | 1300 | 2 | M1 | 650 | 10.02.2025 | 20 | 10.06.2025 | 936.32 | 944.11 | 896.94 |  | M1 is functioning
[9 empty] | M2 | 650 | [7 empty] | M2 is functioning
Total |  |  |  | 63555 | 48419.49 | 15135.51 | 1300 | 2 | [5 empty] | 936.32 | 944.11 | 896.94

## Sudhakar (hidden)
ULB | Quantity to be remediated in MT | Cumulative Quantity remediated till date in MT | Quantity remediated upto 30th April 2025 in MT | Balance Quantity in MT | Capacity of Machine per day to be installed (in MT) | No of Machines | Details of Machinery |  |  | Remarks | 30th April 2025 (Qty in MT) | 1st May 2025 Qty in MT | 2nd May 2025 Qty in MT | 3rd May 2025 Qty in MT | 4th May 2025 Qty in MT | 5th May 2025 Qty in MT | 6th May 2025 Qty in MT | 7th May 2025 Qty in MT | 8th May 2025 Qty in MT | 1st to 8th May 2025 Qty in MT | Status
[7 empty] | No. Machines | Daily capacity | Starting date
M/s Sudhakar Infra Pvt.Ltd.
Tenali | 63550 | 41388.45 | 39685.25 | 22161.55 | 1000 | 2 | M1&M2 | 1000 | 10.02.2025 |  | 905.48 | 0 | 864.15 | 839.05 | [5 empty] | 1703.2